## 3-Month Plan
Project ANU — 3-Month Work Plan
Plain-language tracker for security, performance, MFA, payments, and UI/UX work. Planned period: Monday, 12-Oct-2026 to Thursday, 31-Dec-2026.
Plan start | 2026-10-12T00:00:00.000Z |  | Planning assumptions: • This is a two-resource project. Resource 1 focuses on backend, security, cloud, and performance. Resource 2 focuses on frontend, product, identity, and QA. Some tasks are shared. • Cybersecurity work covers encryption, decryption access, key management, password hashing, and security testing. • Node.js performance work covers a baseline, load testing, and optimization. • MFA requires choosing/configuring a domain or identity provider before implementation. • UI/UX is outsourced. If started Monday, 12-Oct-2026, the initial design delivery is expected around Monday, 26-Oct-2026. • Payment gateway remains a decision item until the business confirms that paid transactions are needed. • Final plan review is scheduled for Thursday, 31-Dec-2026.
Plan end | 2026-12-31T00:00:00.000Z
Total tasks | 26
Done | 0
In progress | 0
Not started | 26
High priority | 20
ID | Area | Task in simple words | What done looks like | Owner | Depends on | Start | Due | Priority | Status | Notes | Days left
1 | Planning | Confirm the 3-month scope and weekly check-ins | Everyone agrees what will be delivered and when | Both resources | None | 2026-10-12T00:00:00.000Z | 2026-10-16T00:00:00.000Z | High | Not started | Use this sheet as the weekly review list | 7
2 | Cybersecurity | List all personal, login, payment, and medical data | A simple data map shows where each type of data is stored | Resource 1 — Backend / Security | Task 1 | 2026-10-12T00:00:00.000Z | 2026-10-16T00:00:00.000Z | High | Not started | Include database, S3, logs, backups, and vendors | 7
3 | Cybersecurity | Review the current security gaps | A short list of risks and fixes is approved | Resource 1 — Backend / Security | Task 2 | 2026-10-13T00:00:00.000Z | 2026-10-23T00:00:00.000Z | High | Not started | Prioritize problems that could expose user or health data | 14
4 | Cybersecurity | Protect data while it is moving | HTTPS/TLS is used for browser, API, database, and storage connections | Resource 1 — Backend / Security | Task 3 | 2026-10-19T00:00:00.000Z | 2026-10-30T00:00:00.000Z | High | Not started | Block insecure HTTP in production | 21
5 | Cybersecurity | Protect stored data and backups | Database, S3 files, and backups use encryption and private access | Resource 1 — Backend / Cloud | Task 3 | 2026-10-19T00:00:00.000Z | 2026-11-06T00:00:00.000Z | High | Not started | Keep buckets private and use short-lived download links | 28
6 | Cybersecurity | Control who can decrypt and view sensitive data | Only approved roles can access decrypted files and records | Resource 1 — Security | Task 5 | 2026-10-26T00:00:00.000Z | 2026-11-13T00:00:00.000Z | High | Not started | Add audit logs for sensitive access | 35
7 | Cybersecurity | Move password storage to Argon2id | New passwords use Argon2id and old hashes migrate after successful login | Resource 1 — Backend | Task 3 | 2026-10-19T00:00:00.000Z | 2026-11-06T00:00:00.000Z | High | Not started | Never encrypt or log passwords | 28
8 | Cybersecurity | Run security tests | Login, storage, access control, rate limits, and secrets are tested | Both resources | Tasks 4-7 | 2026-11-09T00:00:00.000Z | 2026-11-20T00:00:00.000Z | High | Not started | Use staging data only | 42
9 | Node.js | Measure current API speed and resource use | Baseline shows response time, CPU, memory, and error rate | Resource 1 — Backend | Task 1 | 2026-10-19T00:00:00.000Z | 2026-10-30T00:00:00.000Z | High | Not started | Test the busiest endpoints first | 21
10 | Node.js | Run load and stress tests | The team knows how the API behaves with normal and peak traffic | Both resources | Task 9 | 2026-11-02T00:00:00.000Z | 2026-11-13T00:00:00.000Z | High | Not started | Use synthetic users and test files | 35
11 | Node.js | Fix the biggest performance bottlenecks | Slow queries, memory issues, and blocking code are improved | Resource 1 — Backend | Task 10 | 2026-11-09T00:00:00.000Z | 2026-11-27T00:00:00.000Z | High | Not started | Retest after each major fix | 49
12 | Node.js | Repeat the performance test | Results meet agreed response-time and error-rate targets | Both resources | Task 11 | 2026-11-30T00:00:00.000Z | 2026-12-11T00:00:00.000Z | Medium | Not started | Record before-and-after results | 63
13 | MFA | Choose the domain or identity provider for MFA | The MFA provider, domain, email/SMS method, and cost are approved | Resource 2 — Product / Identity | Task 1 | 2026-10-12T00:00:00.000Z | 2026-10-23T00:00:00.000Z | High | Not started | Domain setup is a dependency for this feature | 14
14 | MFA | Configure the MFA domain and provider | The staging domain sends and verifies MFA codes successfully | Resource 1 — Identity / Backend | Task 13 | 2026-10-26T00:00:00.000Z | 2026-11-06T00:00:00.000Z | High | Not started | Use a separate staging configuration | 28
15 | MFA | Build MFA login, recovery, and admin controls | Users can enroll, verify, recover, and disable MFA safely | Both resources | Task 14 | 2026-11-02T00:00:00.000Z | 2026-11-20T00:00:00.000Z | High | Not started | Require MFA for admins first | 42
16 | MFA | Test MFA and prepare rollout | MFA works on common devices and recovery does not weaken security | Both resources | Task 15 | 2026-11-23T00:00:00.000Z | 2026-12-04T00:00:00.000Z | High | Not started | Test lost phone and backup-code scenarios | 56
17 | Payments | Decide whether a payment gateway is needed | Business confirms the payment provider, countries, currencies, and refund rules | Resource 2 — Product / Finance | Task 1 | 2026-10-12T00:00:00.000Z | 2026-10-23T00:00:00.000Z | High | Not started | Keep this as optional until confirmed | 14
18 | Payments | Set up the payment provider in test mode | Sandbox account, webhooks, keys, and test products work | Resource 1 — Backend | Task 17 | 2026-10-26T00:00:00.000Z | 2026-11-06T00:00:00.000Z | Medium | Not started | Never use live keys in development | 28
19 | Payments | Build checkout, payment status, and refunds | A test payment can be created, confirmed, failed, refunded, and recorded | Both resources | Task 18 | 2026-11-02T00:00:00.000Z | 2026-11-20T00:00:00.000Z | Medium | Not started | Verify webhooks instead of trusting the browser | 42
20 | Payments | Test payment security and end-to-end flow | Duplicate payments, failed payments, refunds, and webhook retries are handled | Both resources | Task 19 | 2026-11-23T00:00:00.000Z | 2026-12-04T00:00:00.000Z | Medium | Not started | Use provider test cards only | 56
21 | UI/UX | Prepare the outsourced UI/UX brief | Vendor has screens, user journeys, brand direction, and acceptance criteria | Resource 2 — Product / Design | Task 1 | 2026-10-12T00:00:00.000Z | 2026-10-16T00:00:00.000Z | High | Not started | Outsourced work starts Monday | 7
22 | UI/UX | Outsourced UI/UX initial design delivery | Initial screens and user flows are delivered for review | External UI/UX Partner | Task 21 | 2026-10-12T00:00:00.000Z | 2026-10-26T00:00:00.000Z | High | Not started | Approx. 2 weeks from start | 17
23 | UI/UX | Review and revise the UI/UX design | Approved screens are ready for development handoff | Resource 2 — Product / Design | Task 22 | 2026-10-27T00:00:00.000Z | 2026-11-06T00:00:00.000Z | Medium | Not started | Include accessibility and mobile layouts | 28
24 | Release | Prepare staging release and user acceptance testing | Security, performance, MFA, payment, and UI/UX work is tested together | Both resources | Tasks 8, 12, 16, 20, 23 | 2026-12-07T00:00:00.000Z | 2026-12-18T00:00:00.000Z | High | Not started | Use the staging Supabase project | 70
25 | Release | Fix UAT issues and complete go-live checklist | Open critical issues are closed and owners approve release | Both resources | Task 24 | 2026-12-21T00:00:00.000Z | 2026-12-30T00:00:00.000Z | High | Not started | Keep Dec 31 as the final review date | 82
26 | Review | Year-end review and next-quarter plan | Team records what is done, what remains, and the next priorities | Both resources | Task 25 | 2026-12-31T00:00:00.000Z | 2026-12-31T00:00:00.000Z | Medium | Not started | Use actual progress to reset dates | 83
Formulas:
Days left = [Due]-TODAY()